## 00-Oveview
Milestone Title (Visible to User): | Milestone Description (Visible to User): |  | Entry Criteria: |  | Version: | Complete Message
HIV Estimates Process 2022 | These are the major milestones you will complete as a part of this year's estimates process. Each milestone is made up of tasks. Navigator will walk you through each task, assisting you with instructions and resources along the way. |  | User has an ADR account |  | 0.2 | Congratulations, you have completed this year's estimates process. You may now use your results for other needs such as the PEPFAR data pack, DMPPT2 (for VMMC data where applicable), national reporting, or other needs.
Ref. | Task Title (Visible to User) | Task Test (if test passes, proceed to next test) | If test fails, present this to user: | Resources / Links | Mandatory right now | Test function | Proceed to test (if test fails) | Comments
OVV-01-10 | Welcome to the Navigator | Has the user clicked What's Next? | Welcome to the HIV Estimates Navigator. This tool will guide you step by step through the process of creating your country's HIV Estimates. At each step of the way you will be presented with a task to complete. We ask that you read the instructions carefully and use the extra resources and links provided if necessary to complete the task. When you believe you have completed the task, toggle the task complete/incomplete button in the bottom right by clicking on it, and then click "What's next" to see your next task. |  | 1 | check_manual_confirmation('EST-OVV-01-10-A')
OVV-02-01 | Are you ready to begin the estimates process? | Has the entry criteria for 01-GenEstsDataHMIS been met? | In order to proceed to use the Navigator your country must have: - Collected data from all sites for the time period used in the models; - Compiled and validated the data; - Authorized you to prepare the estimates on behalf of the country. If you are satisfied that the above requirements are met, mark this task and complete and click "What's next?" |  | 1 | check_manual_confirmation('EST-OVV-02-01-A')
OVV-03-01 | Milestone: Preparing Input Data for HIV Estimates | 01-GenEstsDataHMIS |  |  | 1
OVV-04-01 | Milestone: Upload Estimates Inputs Data to ADR | 02-UploadDataADR |  |  | 1
OVV-05-01 | Milestone: Review quality of programme data inputs in ShinyRob | 03-ValidateDataNaomi |  |  | 0
OVV-06-01 | Milestone: Enter Data Into Spectrum | 04-InputDatatoSpectrum |  |  | 1
OVV-07-01 | Milestone: Generate HIV incidence for generalized epidemics using EPP | 05-GenIncidenceEstswithEPP |  |  | 1
OVV-08-01 | Milestone: Generate knowledge of HIV status using Shiny 90 | 06-GenKOSShiny90 |  |  | 1
OVV-09-01 | Milestone: Finalize National HIV Estimates in Spectrum | 07-FinalizeNatlEstsSpectrum |  |  | 1
OVV-10-01 | Milestone: Generate District HIV Estimates Using Naomi | 08-GenSubNatlEstsNaomi |  |  | 1

## 01-GenEstsDataHMIS
Milestone Title (Visible to User): | Milestone Description (Visible to User): |  | Entry Criteria: |  | Version:
Preparing Input Data for HIV Estimates | In this milestone, you will prepare and place the required input data in the Inputs Package needed to generate HIV estimates. You should use the best, highest quality, and most complete input data you have available to you for the estimates process. |  | Country has collected data from all sites for the time period used in the models Data are compiled and validated by country (e.g., MOH) authorities. The user is authorized to prepare estimates on behalf of the country |  | 0.2
Ref. | Task Title (Visible to User) | Task Test (if test passes, proceed to next test) | If test fails, present this to user: | Resources / Links | Mandatory right now | Comments | Proceed to test (if test fails) | Test function
GEN-01-10 | Ensure programme data are complete in your national health information system (e.g., DHIS2) | Have all programme data required for estimates been completed and are they available in the national health information system? | The majority of delays and challenges with the estimates process are related to the preparation of data inputs. Best practice suggests that high quality data inputs should be prepared prior to beginning your estimates. Ensure all programme data are available in your country's national health management information system (e.g., DHIS2), reviewed for quality, validated by the relevant authorities, and ready for use in this year's estimates process. To learn more about the programme data required, see Guide 8, Data Quality, Indicator Element Matrix. | Guide 8, Data Quality, Indicator Element Matrix https://hivtools.unaids.org/hiv-estimates-training-material-en/ |  | MM: Add sheet to HIV tools page and put link to that sheet here MM: Add link to video on data preparation. Training materials ID: G.10 |  | check_manual_confirmation('EST-GEN-01-10-A')
GEN-02-01 | Review the quality of and validate your programme data using UNAIDS Guide 6, Data Quality Standards of Practice. | Has the country team conducted data quality procedures on each of the required data inputs using Guide 6, Data Quality Standards of Practice? | The greatest impediment to a successful estimates process is poor quality programme data. The most important thing you can do before you begin is review the quality of your programme data. There are specific analyses recommended to assess the quality of your program data. These analyses are available in Guide 6, Data Quality Standards of Practice. Table 2 provides specific analyses for the different programme inputs to ensure you start the estimates process with high quality inputs. ShinyRob is another tool available to users for assessing data quality. This step will be completed after data are uploaded to ADR. | Guide 6, Data Quality Standards of Practice https://hivtools.unaids.org/hiv-estimates-training-material-en/ |  | MM: training materials ID: D.8 |  | check_manual_confirmation('EST-GEN-02-01-A')
GEN-03-01 | Update your ANC programme data file with data from the current reporting period | Has user updated ANC data file? | Before you upload your Inputs Package to ADR, ensure you have updated the data files for the current reporting period. **Update** your programme data files for ANC. UNAIDS recommends beginning with last year's final Inputs Package and only updating the files for the current reporting period. You can learn more about the data elements required in Guide 8 Data Quality, Indicator Elements Matrix. | AIDS Data Repository https://adr.unaids.org/ Guide 8, Data Quality, Indicator Element Matrix https://hivtools.unaids.org/hiv-estimates-training-material-en/ |  | @Fjelltopp - plz link to the user's organization page. |  | check_manual_confirmation('EST-GEN-03-01-A')
GEN-04-01 | Update your ART programme data file with data from the current reporting period | Has user updated ART data file? | Before you upload your Inputs Package to ADR, ensure you have updated the data files for the current reporting period. **Update** your programme data files for ART. UNAIDS recommends beginning with last year's final Inputs Package and only updating the files for the current reporting period. You can learn more about the data elements required in Guide 8 Data Quality, Indicator Elements Matrix. | AIDS Data Repository https://adr.unaids.org/ Guide 8, Data Quality, Indicator Element Matrix https://hivtools.unaids.org/hiv-estimates-training-material-en/ |  |  |  | check_manual_confirmation('EST-GEN-04-01-A')
GEN-05-01 | If relevant, update your Voluntary Male Medical Circumcision (VMMC) programme data file with data from the current reporting period | Has user updated VMMC data file? | Before you upload your Inputs Package to ADR, ensure you have updated the data files for the current reporting period. **Update** your programme data files for VMMC (if relevant). UNAIDS recommends beginning with last year's final Inputs Package and only updating the files for the current reporting period. If you are not using VMMC data for your estimates, you can market this task as complete. You can learn more about the data elements required in Guide 8 Data Quality, Indicator Elements Matrix. | AIDS Data Repository https://adr.unaids.org/ Guide 8, Data Quality, Indicator Element Matrix https://hivtools.unaids.org/hiv-estimates-training-material-en/ |  |  |  | check_manual_confirmation('EST-GEN-05-01-A')
GEN-06-01 | Update your Shiny 90 HIV Testing programme data file with data from the current reporting period | Has user updated Shiny 90 HIV Testing data file? | Before you upload your Inputs Package to ADR, ensure you have updated the data files for the current reporting period. **Update** your programme data files for HIV Testing in the Shiny 90 data file. UNAIDS recommends beginning with last year's final Inputs Package and only updating the files for the current reporting period.You can learn more about the data elements required in Guide 8 Data Quality, Indicator Elements Matrix. If you are not planning to use Shiny 90 to estimate your Knowledge of Status figures, mark this task complete in Navigator. | AIDS Data Repository https://adr.unaids.org/ Guide 8, Data Quality, Indicator Element Matrix https //hivtools.unaids.org/hiv-estimates-training-material-en/ |  |  |  | check_manual_confirmation('EST-GEN-06-01-A')
GEN-07-01 | Review your Shiny 90 Survey data file in your Inputs Package | Has user reviewed their Shiny 90 survey data file? | UNAIDS has placed a *Shiny 90 survey* file in your Inputs Package in the AIDS Data Repository (ADR). Before we begin the estimates process, please review this file. If you are satisfied with the data in this file, mark this task complete. If you see problems with this file, contact UNAIDS or one of its partners to have it corrected. If you are not planning to use Shiny 90 to estimate your Knowledge of Status figures, mark this task complete in Navigator. | AIDS Data Repository https://adr.unaids.org/ |  |  |  | check_manual_confirmation('EST-GEN-07-01-A')
GEN-08-01 | Review your Naomi Survey data file in your Inputs Package | Has user reviewed their Naomi survey data file? | UNAIDS has placed a *Naomi survey* file in your Inputs Package in the AIDS Data Repository (ADR). Before we begin the estimates process, please review this file. If you are satisfied with the data in this file, mark this task complete. If you see problems with this file, contact UNAIDS or one of its partners to have it corrected.If you are not planning to use Naomi to produce district-level HIV estimates, mark this task complete in Navigator. | AIDS Data Repository https://adr.unaids.org/ |  |  |  | check_manual_confirmation('EST-GEN-08-01-A')
GEN-09-01 | Review your area boundary file in your Inputs Package | Has user reviewed their area boundary data file? | UNAIDS has placed an *Area Boundary* data file in your Inputs Package in the AIDS Data Repository (ADR). Before we begin the estimates process, please review this file. If you are satisfied with the data in this file, mark this task complete. If you see problems with this file, contact UNAIDS or one of its partners to have it corrected. | AIDS Data Repository https://adr.unaids.org/ |  |  |  | check_manual_confirmation('EST-GEN-09-01-A')
GEN-10-01 | Review your Population file in your Inputs Package | Has user reviewed their population data file? | UNAIDS has placed a *Population* data file in your Inputs Package in the AIDS Data Repository (ADR). Before we begin the estimates process, please review this file. If you are satisfied with the data in this file, mark this task complete. If you see problems with this file, contact UNAIDS or one of its partners to have it corrected. | AIDS Data Repository https://adr.unaids.org/ |  |  |  | check_manual_confirmation('EST-GEN-10-01-A')

## 02-UploadDataADR
Milestone Title (Visible to User): | Milestone Description (Visible to User): |  | Entry Criteria: |  | Version:
Upload Estimates Inputs Package Data Files to ADR | Once you have prepared your Inputs Package data file, you can upload the files to your organization/country on the AIDS Data Repository (ADR). There are many advantages to using ADR, including integration with key estimates models such as ShinyRob and Naomi. Before you begin this step, you should be sure you have updated all required programme data files for the current reporting period (e.g., ANC, ART, Shiny 90 HIV testing, and VMMC where relevant). You can also review your other data files (e.g., surveys, population, area boundary). You will need to have an ADR user account and be associated with an organization (country) with an editor role. |  | Data input files are available User has an ADR account associated with a country organization in ADR User has at least editor role assigned within the country organization |  | 0.2
Ref. | Task Title (Visible to User) | Task Test (if test passes, proceed to next test) | If test fails, present this to user: | Resources / Links | Mandatory right now | Comments | Proceed to test (if test fails) | Test function
ADR-01-10 | Check that the required data has been preloaded into your ADR dataset | Does the user have geojson, survey data, population data, shiny90 survey data, spectrum file in their dataset? | Your estimates dataset in the ADR should already have the following data preloaded into it: - Spectrum file - Geograph data (subnational area boundaries) - Survey data - Population data If any of this data is missing or incorrect, please speak to a facilitator to help you compile this missing data and upload it to the ADR. |  |  | JB: This is an automatic check, so will only be shown to the user if they are missing expected data. It's just a proposal Can easily remove. |  | check_resource_key(['inputs-unaids-geographic', 'inputs-unaids-survey', 'inputs-unaids-population', 'inputs-unaids-spectrum'], 'url', '.*')
ADR-01-11 | Upload data inputs to the ADR using the required templates | Are the required inputs uploaded to the ADR? | UNAIDS strongly recommends the use of the AIDS Data Repository (ADR) to store your estimates data, both inputs and outputs. Using ADR provides a number of advantages and efficiencies for your estimates process, including a secure location to store your data files as well as automated validation function to ensure your data meet formatting and minimum data quality requirements before beginning the data. Access your organization on ADR and find this year's inputs package. Upload each of the required files for this year's estimates process in the required format. You should ensure you have uploaded new data for the following inputs: - Shiny90 HIV Testing Data - ART Data - ANC Data **To upload a new input to the ADR:** - Open your estimates 2022 Inputs Package in the ADR - Drag and drop your data input file into the centre of the ADR web page. - A pop up will open with the name of your file in it. - In the dropdown next to the filename , select which data input you are uploading. - Click "Upload Files" |  |  |  |  | check_manual_confirmation('EST-ADR-01-11-A')
ADR-02-01 | Upload your Shiny 90 HIV testing data files to ADR | Is user's Shiny 90 HIV Testing data file uploaded to ADR in the required format? | Your ADR dataset should include a *Shiny 90 HIV Testing Data* resource. UNAIDS strongly recommends the use of the AIDS Data Repository (ADR) to store your estimates data, both inputs and outputs. Using ADR provides a number of advantages and efficiencies for your estimates process, including a secure location to store your data files as well as automated validation function to ensure your data meet formatting and minimum data quality requirements before beginning the estimates process. Access your organization on ADR and find this year's Inputs Package. Upload the *updated Shiny 90 HIV testing data file* in the required format. **To upload your Shiny 90 HIV Testing data file to the ADR:** - Open your estimates 2022 Inputs Package in the ADR - Under *Missing Resources* find "Shiny 90 Testing Data" and click *Add Data* - Drag your data file into the file upload zone - Add any useful notes about the file under *Description* - Confirm the format field is correct - If you wish to share the file with someone outside your organisation you can do so under *Access Restriction* - Click "Add" to upload the file |  | 1 |  |  | check_resource_key('inputs-unaids-hiv-testing', 'url', '.*')
ADR-03-01 | Upload your ART programme data file to your Inputs Package on the ADR | Has the user uploaded an ART data file? | Your ADR dataset should include an *ART Data* resource. UNAIDS strongly recommends the use of the AIDS Data Repository (ADR) to store your estimates data, both inputs and outputs. Using ADR provides a number of advantages and efficiencies for your estimates process, including a secure location to store your data files as well as automated validation function to ensure your data meet formatting and minimum data quality requirements before beginning the estimates process. Access your organization on ADR and find this year's Inputs Package. Upload the *updated ART data file* in the required format. **To upload your ART data to the ADR:** - Open your estimates 2022 Inputs Package in the ADR - Under *Missing Resources* find "ART Data" and click *Add Data* - Drag your ART template file into the file upload zone - Add any useful notes about the file under *Description* - Confirm the format field is correct - If you wish to share the file with someone outside your organisation you can do so under *Access Restriction* - Click "Add" to upload the file | AIDS Data Repository https://adr.unaids.org/ | 1 |  |  | check_resource_key('inputs-unaids-art', 'url', '.*')
ADR-04-01 | Upload your ANC data file to your Inputs Package on the ADR | Has the user uploaded an ANC data file? | Your ADR dataset should include an *ANC Data* resource. UNAIDS strongly recommends the use of the AIDS Data Repository (ADR) to store your estimates data, both inputs and outputs. Using ADR provides a number of advantages and efficiencies for your estimates process, including a secure location to store your data files as well as automated validation function to ensure your data meet formatting and minimum data quality requirements before beginning the estimates process. Access your organization on ADR and find this year's Inputs Package. Upload the *updated ANC data file* in the required format. **To upload your ANC data file to the ADR:** - Open your estimates 2022 Inputs Package in the ADR - Under *Missing Resources* find "ANC Data" and click *Add Data* - Drag your ANC template file into the file upload zone - Add any useful notes about the file under *Description* - Confirm the format field is correct - If you wish to share the file with someone outside your organisation you can do so under *Access Restriction* - Click "Add" to upload the file | AIDS Data Repository https://adr.unaids.org/ | 1 |  |  | check_resource_key('inputs-unaids-anc', 'url', '.*')
ADR-05-01 | Upload the VMMC data file to your Inputs Package on the ADR | Is the VMMC data file uploaded to ADR in the required format? | This requirement only applies to the 15 countries that are prioritized for VMMC. The data will be used to create district level coverage estimates of VMMC in your country. UNAIDS strongly recommends the use of the AIDS Data Repository (ADR) to store your estimates data, both inputs and outputs. Using ADR provides a number of advantages and efficiencies for your estimates process, including a secure location to store your data files as well as automated validation function to ensure your data meet formatting and minimum data quality requirements before beginning the estimates process. Access your organization on ADR and find this year's Inputs Package. Upload each of the required files for this year's estimates process in the required format. If you are *not* from one of the 15 countries who are prioritizing VMMC, you can mark this task complete to skip it. | AIDS Data Repository https://adr.unaids.org/ | 1 |  |  | check_manual_confirmation('EST-ADR-05-01-A')
ADR-06-01 | Ensure ADR has validated each of the data files in your Inputs Package | Are all uploaded data files for Shiny 90, Naomi, and VMMC (if applicable) valid in ADR? | ADR provides a cursory data quality check on all files in the Inputs Package. Be sure to confirm the green "Valid" badge next to each file. If any files are missing the green "valid" badge, be sure to review the data issues identified by ADR and correct them. If any changes are made to the data in the estimates data files, ensure changes are cascaded to the source systems (e.g., DHIS2) as needed. Once data files are uploaded and valid in ADR, you may proceed to ShinyRob to conduct more thorough data quality reviews. | AIDS Data Repository https://adr.unaids.org/ | 1 |  |  | check_dataset_valid()

## 03-ValidateDataNaomi
Milestone Title (Visible to User): | Milestone Description (Visible to User): |  | Entry Criteria: |  | Version:
Review quality of programme data inputs using the *Review Inputs* function in Naomi | The quality of data inputs is one of the most influential determinants of your HIV estimates. The Data Review function in Naomi was developed to assist countries to identify and resolve data quality issues within programme data inputs before they are used by estimates models. UNAIDS strongly recommends country teams review and validate their programme data inputs using ShinyRob prior to beginning work in the models. |  | User has ADR account and ADR key and Naomi account User is associated with a country organization in ADR Country’s Inputs Package files for ANC and ART, including area hierarchy dataset, have been uploaded and have an ADR validation |  | 0.2
Ref. | Task Title (Visible to User) | Task Test (if test passes, proceed to next test) | If test fails, present this to user: | Resources / Links | Mandatory right now | Comments | Proceed to test (if test fails) | Test function
ROB-01-CK |  | ADR-03-01, ADR-04-01 complete? |  |  | 1 | not a user-facing task check; required to import data from ADR |  | check_not_skipped(['EST-ADR-03-01-A', 'EST-ADR-04-01-A'])
ROB-02-01 | Create a Naomi user account | Does the user already have a Naomi account? | In order to use the Naomi Inputs Review Function, UNAIDS recommends you create a Naomi user account. A Naomi user account has multiple advantages, including integration with ADR and direct access to your Inputs Package, project saving, and sharing of draft and final project results. If you do not already have an account, you may request one by completing the brief Naomi user account request form. Responses should be immediate, especially during the time of estimates workshops. If you prefer, you may use Naomi as a guest, but it is not recommended. | Naomi user account request form https://forms.office.com/r/7S9EMigGr4 | 1 |  |  | check_manual_confirmation('EST-ROB-02-01-A')
ROB-03-01 | Log into Naomi | Is the user logged in to Naomi? | In order to take full advantage of Naomi's functionality, UNAIDS recommends you log into the system with your user account. There are many advantages to logging into Naomi such as integration with ADR and direct access to your estimates Inputs Package, project saving, and sharing of draft and final project results.. If you do not log in, you will not be able to pull your data from ADR nor save projects and versions. To log into Naomi, go to naomi.unaids.org. Click the 'Log in' button in the upper right corner of the home page to enter your login details. |  | 1 |  |  | check_manual_confirmation('EST-ROB-03-01-A')
ROB-04-01 | Create a project in Naomi for the current reporting period | Has the user created a project in Naomi? | The first step to using Naomi, even for the Inputs Review function, is to create a project. Each Naomi project will have its own data and settings. If you are logged in, you can save multiple projects and test different data and model options for comparison. To create a project, simply enter a name for the project and click the 'Create Project' button. |  | 1 |  |  | check_manual_confirmation('EST-ROB-04-01-A')
ROB-05-01 | Select the Inputs Packages you would like to review | Has user selected geographic data package, ART data package, and ANC data package? | In order to utilize the powerful data quality analyses provided by Naomi's Inputs Review function, you must select the relevant Inputs Package for this year, including geographic data package (named area boundary file in ADR), ART data package, and ANC data package. | AIDS Data Repository https://adr.unaids.org/ | 1 |  |  | check_manual_confirmation('EST-ROB-05-01-A')
ROB-06-01 | Review time series results for your ART data file | Has user reviewed all plot types for their ART and ANC data files and corrected all anomolies? | The Naomi Inputs Review function provides a number of powerful visualizations to help country teams identify data quality problems. UNAIDS recommends country teams view each of the plot options available for ART and ANC. Selecting these different options will present you with each district's data trends for the years included in your data file. Potential data anomolies will be highlighted by red lines. It's important to document any anomolies with your team to investigate further. Engage your district counterparts to investigate and resolve anomolies. Remember, data quality issues can have a major impact on your estimates. **Your estimates outputs are only as good as the quality of your Inputs Package. UNAIDS strongly recommends correcting any erroneous data in the source system and inputs templates prior to proceeding with your estimates process.** Once your data files have been corrected, you may upload them to ADR in lieu of the previous versions with errors. Once you are fully satisfied with the quality of all data files, you may proceed with the estimates process, starting with Milestone 4 - Enter Data into Spectrum. |  | 1 |  |  | check_manual_confirmation('EST-ROB-06-01-A')

## Old 03 (ValidateDataShinyRob)
Milestone Title (Visible to User): | Milestone Description (Visible to User): |  | Entry Criteria: |  | Version:
Review quality of programme data inputs using ShinyRob | The quality of data inputs is one of the most influential determinants of your HIV estimates. ShinyRob was developed to assist countries to identify and resolve data quality issues within programme data inputs before they are used by estimates models. UNAIDS strongly recommends country teams review and validate their programme data inputs using ShinyRob prior to beginning work in the models. |  | User has ADR account and ADR key and Naomi account User is associated with a country organization in ADR Country’s Inputs Package files for ANC and ART, including area hierarchy dataset, have been uploaded and have an ADR validation |  | 0.2
Ref.Old | Ref. | Task Title (Visible to User) | Task Test (if test passes, proceed to next test) | If test fails, present this to user: | Resources / Links | Mandatory right now | Comments | Proceed to test (if test fails) | Test function
ROB-01 | ROB-01-10 | Confirm all Inputs Package data files have a green valid badge in ADR | Are input files (ANC, ART, area boundary files) in ADR and marked with a green valid badge (i.e., is ADR-06-01 true)? | In order to use ShinyRob, you must upload three data files to your estimates Inputs Package for this year. To upload your files, access your organization on ADR and find this year's Inputs Package. Upload each of the required files for this year's estimates process in the required format. *UNAIDS strongly recommends you use your final data files from last year and simply update them with this data from the current reporting period.* Be sure to confirm the green "Valid" badge next to each file. If any files are missing the green "valid" badge, review the data issues identified by ADR and correct them. If any changes are made to the data in the data files, ensure changes are cascaded to the source systems (e.g., DHIS2) as needed. Once data are uploaded and valid in ADR, you may proceed to ShinyRob to conduct thorough data quality reviews. | AIDS Data Repository https://adr.unaids.org/ | 1 |  |  | check_not_skipped(['EST-ADR-04-A', 'EST-ADR-04A-A', 'EST-ADR-04B-A', 'EST-ADR-04C-A', 'EST-ADR-04D-A', 'EST-ADR-04E-A', 'EST-ADR-06-A'])
ROB-02 | ROB-02-01 | Submit your ADR key to ShinyRob | Has user submitted ADR key to ShinyRob? | ShinyRob was developed by UNAIDS to assist country teams to review the quality of their programme data prior to using the data in the estimates models. ShinyRob accesses country programme data directly from your estimates Inputs Package on ADR. To allow ShinyRob to access your Inputs Package, enter your ADR key. Your ADR key can be found in the left side of your profile page on ADR. Once you're logged into ADR, simply click your name at the top of any page and look for your ADR key in the bottom left of the page. Copy the key and paste it into ShinyRob to select this year's Inputs Package for review. | ShinyRob https://shinyrob.unaids.org/ AIDS Data Repository https://adr.unaids.org/me | 1 |  |  | check_manual_confirmation('EST-ROB-02-A')
ROB-CK-02 | ROB-03-01-CK |  | ADR-03-01,ADR-04-01 complete? |  |  | 1 | not a user-facing task check; required to import data from ADR |  | check_not_skipped(['EST-ADR-04-A', 'EST-ADR-04A-A', 'EST-ADR-04B-A', 'EST-ADR-04C-A', 'EST-ADR-04D-A', 'EST-ADR-04E-A', 'EST-ADR-06-A'])
ROB-03 | ROB-04-01 | Select the Inputs Packages you would like to review | Has user selected geographic data package, ART data package, and ANC data package? | In order to utilize the powerful data quality analyses provided by ShinyRob, you must select the relevant Inputs Package for this year, including geographic data package (named area boundary file in ADR), ART data package, and ANC data package. | ShinyRob https://shinyrob.unaids.org/ AIDS Data Repository https://adr.unaids.org/ | 1 |  |  | check_manual_confirmation('EST-ROB-03-A')
ROB-04 | ROB-05-01 | Ensure ShinyRob has validated your geographic (area boundary), ART, and ANC data files | Has ShinyRob validated the three packages (geographic, ART, ANC)? | Once selected, ShinyRob will conduct a cursory formatting review on the files and note each one as "valid". If they fail the validity test, you must return to ADR and the source files in the Inputs Package to correct the errors before ShinyRob can visualize the data. | ShinyRob https://shinyrob.unaids.org/ AIDS Data Repository https://adr.unaids.org/ | 1 | @Fjelltopp - can we link directly to their organization Inputs Package? |  | check_manual_confirmation('EST-ROB-04-A')
ROB-05 | ROB-06-01 | Verify and/or correct any data anomoloies | Has user reviewed all programme data and corrected or verified any anomolies for use in HIV estimates? | Once your Inputs Packages are validated, you may review all data at the district level by clicking the "Visualize Data" link in the upper left of the screen. You may scroll through the different analyses in the tabs. ShinyRob will highlight any anomolies in your data with red lines (e.g., rapid quarter-to-quarter changes in values or ratios) to help you identify data quality issues. It's important to document any anomolies with your team to investigate further. Engage your district counterparts to investigate and resolve anomolies. Remember, data quality issues can have a major impact on your estimates. **Your estimates outputs are only as good as the quality of your Inputs Package. UNAIDS strongly recommends correcting any erroneous data in the source system and inputs templates prior to proceeding with your estimates process.** Once your data files have been corrected, you may upload them to ADR in lieu of the previous versions with errors. Once you are fully satisfied with the quality of all data files, you may proceed with the estimates process, starting with Milestone 4 - Enter Data into Spectrum. |  | 1 |  |  | check_manual_confirmation('EST-ROB-05-A')

## 04-InputDatatoSpectrum
Milestone Title (Visible to User): | Milestone Description (Visible to User): |  | Entry Criteria: |  | Version:
Enter Data Into Spectrum | You will be using the Spectrum model for many of the upcoming tasks. The first milestone in Spectrum will have you entering data inputs into the software before estimating HIV incidence and knowledge of status. You will complete your Spectrum results in a second Spectrum milestone. For countries producing sub-national (e.g., provincial) Spectrum estimates, the tasks below must be completed for each Spectrum file. |  | User has correct Spectrum software available, has last year’s Spectrum file, and PMTCT and ART program data available |  | 0.2
Ref. | Spectrum Check File Ref | Task Title (Visible to User) | Task Test (if test passes, proceed to next test) | If test fails, present this to user: | Resources / Links | Mandatory right now | Comments | Proceed to test (if test fails) | Test function
SPE-01-10 |  | Confirm you are using the Spectrum AIM client software installed on a computer | Will user use Spectrum AIM client software? | Spectrum has two versions available for countries - i) Spectrum AIM client software available for download and installation on a team member's computer or ii) Spectrum Web, a browser and cloud version of the software. If you are planning to use the client software, you may proceed to the next task. To use Spectrum Web, you must first create user account. If you do not have an existing user account, you can create one on Spectrum Web. Once you have selected, you may mark this task complete in Navigator. | Spectrum https://aim.spectrumweb.org/ |  | S4: Note this task recommends the user mark this task complete regardless of the Spectrum version they want to use. This assumes the instructions below are suitable to both versions. |  | check_manual_confirmation('EST-SPE-01-10-A')
SPE-02-01 |  | Ensure you are using the latest version of Spectrum AIM | Does user have the latest version of Spectrum AIM? | UNAIDS strongly recommend using the latest version of Spectrum AIM for your estimates. Older versions may be incompatible with the current process. Further, you may miss out on new functionality developed in the most recent version. To download and install the most recent version, visit the Spectrum software link below. On the right side of the page, find the AIM Releases section and download the most recent version. Once you have the file on your laptop, you can double click the *exe* file and follow the normal installation instructions. | Spectrum software https://www.avenirhealth.org/software-spectrum.php | 1 |  |  | check_manual_confirmation('EST-SPE-02-01-A')
SPE-03-01 |  | Open your Spectrum file | Does user have a Spectrum file for this year's estimates? | After you've logged in (or opened your Spectrum AIM program on your computer), you must upload your existing Spectrum projection file. If your country will only use one Spectrum file for the national level, you only need to do this once. If you will use separate Spectrum files for different geographic areas (optional), you will update a Spectrum file for each area. |  | 1 |  |  | check_manual_confirmation('EST-SPE-03-01-A')
SPE-04-01 |  | Ensure population estimates in your Spectrum file match official estimates | Do Spectrum file population estimates match official estimates in your Spectrum file? | By default Spectrum uses the UN World Population Projection population estimates. You can either use these default data or use official country population census data. You can select and edit population data in the Projection Manager by selecting the "Default Data" option. For countries with sub-national Spectrum estimates (optional), this step applies to each file. |  |  | JS: The user has to do this. There is not way for Spectrum to know. |  | check_manual_confirmation('EST-SPE-04-01-A')
SPE-05-01 | PMTCT_current | Enter PMTCT data for the current reporting year into Spectrum | Does the user's Spectrum file have current estimates year data for PMTCT [required / optional data elements available in Indicator Element Matrix]? | Spectrum requires up-to-date PMTCT programme data for the reporting period. These data are required for each Spectrum file. You can find all required data elements in the Guide 8, Data quality, Indicator Element Matrix. It is highly recommended you finalize your programme data before beginning the Spectrum process. If edits to PMTCT programme data are required later in the process, you will have to return to this step. For countries with sub-national Spectrum estimates (optional), this step applies to each file. | Guide 8, Data quality, Indicator Element Matrix https://hivtools.unaids.org/hiv-estimates-training-material-en/ |  |  |  | check_manual_confirmation('EST-SPE-05-01-A')
SPE-06-01 |  | Update breastfeeding patterns in Spectrum | Has user updated Breastfeeding Pattern in their Spectrum file? | The duration of breastfeeding is important for understanding how long a child is exposed to possible vertical transmission. Spectrum has prepopulated data that reflect data from surveys in your country on breastfeeding patterns. These data are updated periodically to reflect new surveys. On the PMTCT tab, please click on Breastfeeding then Read survey data button to update the breastfeeding patterns among women not receiving ARVs. A pop up button will ask if you want to update these data for women Receiving ARVs at the same time. If you select Yes it will update both ‘Not receiving ARVs’ and ‘Receiving ARVs’. Alternatively, if you have data from your PMTCT programme on breastfeeding duration you could enter that for the women Receiving ARVs. |  |  | 05/Nov - updated with MM's text |  | check_manual_confirmation('EST-SPE-06-01-A')
SPE-07-01 |  | Update ANC testing data in Spectrum | Has user updated ANC testing data in their Spectrum file for current reporting period [required / optional data elements available in Indicator Element Matrix]? | Although not mandatory becasue it does not impact the model, UNAIDS suggests user provide up-to-date ANC Testing programme data for the reporting period to check the quality of the ANC data. This information helps to identify issues with prevalence data for your estimates. You can find all required data elements in the Guide 8, Data quality, Indicator Element Matrix. It is highly recommended you review these programme data before beginning the incidence curve fitting process. | Guide 8, Data quality, Indicator Element Matrix https://hivtools.unaids.org/hiv-estimates-training-material-en/ |  |  |  | check_manual_confirmation('EST-SPE-07-01-A')
SPE-08-01 | MaleART_current, FemaleART_current | Update Adult ART data in Spectrum | Has user updated adult ART data in their Spectrum file for current reporting period [required / optional data elements available in Indicator Element Matrix]? | Spectrum requires up-to-date Adult ART programme data for the reporting period for estimating treatment coverage and for estimating incidence. You should update the ART data before running your incidence curve. Data on the number newly initiated on ART and lost to follow up can improve the precision of some of the outputs from Spectrum. If those data are available be sure to include them. You can find all required data elements in the Guide 8, Data quality, Indicator Element Matrix. If edits to the ART programme data are required later in the process, you will have to rerun your incidence curve fitting. | Guide 8, Data quality, Indicator Element Matrix https://hivtools.unaids.org/hiv-estimates-training-material-en/ |  |  |  | check_manual_confirmation('EST-SPE-08-01-A')
SPE-09-01 |  | Confirm ART data entered in Spectrum match the Naomi ART data input file on ADR | Do the sum totals for ART - including pediatric, male adults, and female adults - from the user's Spectrum file match the data in the country's Naomi ART file? | Countries should be using a single, validated source of information for data used in different estimates models, even if some models require sub-national data (e.g., Naomi) and others use national-level data (e.g., Spectrum in most cases). ART data are one such source used by both Naomi and Spectrum. The ART totals you have entered in Spectrum for pediatric, adult female, and adult male populations must match the sum of the subnational ART data for the same populations in your Naomi Inputs Package. *If these two data sources do not match, please review and correct so what you enter in Spectrum is the same as what you have in your Naomi inputs file.* For countries producing provincial-level Spectrum estimates, ensure that the district data for Naomi match the provincial Spectrum files to which the districts belong. |  |  | S4: Added 27/Oct. |  | check_manual_confirmation('EST-SPE-09-01-A')
SPE-10-01 | PedART_current | Update Pediatric ART data in Spectrum for the current reporting period | Has user updated pediatric ART data in their Spectrum file for current reporting year [required / optional data elements available in Indicator Element Matrix]? | Spectrum requires up-to-date Pediatric ART programme data for the reporting period. You can find all required data elements in the Guide 8, Data quality, Indicator Element Matrix. It is highly recommended you finalize your programme data before beginning the Spectrum process. If edits to ART programme data are required later in the process, you will have to return to this step. | Guide 8, Data quality, Indicator Element Matrix https://hivtools.unaids.org/hiv-estimates-training-material-en/ |  |  |  | check_manual_confirmation('EST-SPE-10-01-A')
SPE-11-01 | PedVS_current,MaleVS_current,FemaleVS_current | Update viral load suppression data in Spectrum for the current reporting period for adult females and males and pediatric populations | Spectrum file has updated viral suppression data in Spectrum for current reporting period [required / optional data elements available in Indicator Element Matrix]? | Spectrum requires up-to-date adult and pediatric viral load suppression programme data for the reporting period. You can find all required data elements in the Guide 8, Data quality, Indicator Element Matrix. It is highly recommended you finalize your programme data before beginning the Spectrum process. Enter the best, most up-to-date viral load suppression data you have for adult female, adult male, and pediatric populations. |  |  | JS: In the Data Checker |  | check_manual_confirmation('EST-SPE-11-01-A')
SPE-12-CK |  |  | Are SPE-05-01,SPE-07-01,SPE-08-01,SPE-10-01,SPE-11-01 complete? |  |  | 1 | Not a user-facing task MM: SPE-06 is not required. i have removed |  | check_not_skipped(['EST-SPE-05-01-A', 'EST-SPE-07-01-A', 'EST-SPE-08-01-A', 'EST-SPE-10-01-A', 'EST-SPE-11-01-A'])
SPE-12-01 | AdultProgression_default,AdultDistNI_default,ARTMortNoART_default,ARTMortART_default | Confirm default values for adult parameters under Advanced Options | Has the user confirmed that the default values for adult parameters under Advanced Options are updated? | To produce accurate estimates, Spectrum relies on a number of assumptions that are summarized under Advanced Options. These parameters are updated every year as new research and evidence is available on those parameters. For Spectrum on the Desktop update the parameters by selecting Advanced Options > Adult Parameters > Restore defaults. For Spectrum on the web: enter Advanced Options and confirm the default selections for adult parameters. If you see values in red font, the parameters have not been updated. To learn more about the Advanced Options, see the Spectrum training materials. | Spectrum training materials https://hivtools.unaids.org/hiv-estimates-training-material-en/ |  |  |  | check_manual_confirmation('EST-SPE-12-01-A')
SPE-13-01 | ChildProgression_default,ChildDistNI_default,ChildMortNoART_default,ChildMortART_default | Confirm default values for pediatric parameters under Advanced Options | Has the user confirmed that the default values for pediatric parameters under Advanced Options are correct? | To produce accurate estimates, Spectrum relies on a number of assumptions that are summarized under Advanced Options. These parameters are updated every year as new research and evidence is available on those parameters. For Spectrum on the Desktop update the parameters by selecting Advanced Options > Pediatric Parameters > Restore defaults. For Spectrum on the web: enter Advanced Options and confirm the default selections for pediatric parameters. If you see values in red font, the parameters have not been updated. To learn more about the Advanced Options, see the Spectrum training materials. | Spectrum training materials https://hivtools.unaids.org/hiv-estimates-training-material-en/ |  |  |  | check_manual_confirmation('EST-SPE-13-01-A')
SPE-14-01 | FRRCD4_default,FRRageNoART_default,FRRageART_default | Confirm default values for Fertility Rate Ratios under Advanced Options | Has the user confirmed that the default values for Fertility Rate Ratios under Advanced Options are correct? | To produce accurate estimates, Spectrum requires the correct options are selected under Advanced Options. Enter Advanced Options in Spectrum Web and confirm the default selections for the "HIV-related fertility reductions" are correct for your country. They must be confirmed for CD4, on ART, and off ART. To learn more about the Advanced Options, see the Spectrum training materials. | Spectrum training materials https://hivtools.unaids.org/hiv-estimates-training-material-en/ |  |  |  | check_manual_confirmation('EST-SPE-14-01-A')
SPE-15-01 | MTCTtrans_default | Confirm default values for MTCT probabilities under Advanced Options | Has the user confirmed that the default values for mother-to-child transmission probabilities under Advanced Options are correct? | To produce accurate estimates, Spectrum requires the correct options are selected under Advanced Options. Enter Advanced Options in Spectrum Web and confirm the default selections for the "MTCT Transmission Probabilities" are correct for your country. To learn more about the Advanced Options, see the Spectrum training materials. | Spectrum training materials https://hivtools.unaids.org/hiv-estimates-training-material-en/ |  |  |  | check_manual_confirmation('EST-SPE-15-01-A')
SPE-16-01 | ARTallocation_default | Confirm default values for new ART allocation method under Advanced Options | Has the user confirmed that the default values for the allocation method for new ART patients under Advanced Options is correct? | To produce accurate estimates, Spectrum requires the correct options are selected under Advanced Options. Enter Advanced Options in Spectrum Web and confirm the default selection for the "allocation method for new ART patients" is correct for your country. To learn more about the Advanced Options, see the Spectrum training materials. | Spectrum training materials https://hivtools.unaids.org/hiv-estimates-training-material-en/ |  |  |  | check_manual_confirmation('EST-SPE-16-01-A')
SPE-17-CK |  |  | Are SPE-12-01, SPE-13-01, SPE-14-01, SPE-15-01, SPE-16-01 complete? |  |  | 1 | Not a user-facing task |  | check_not_skipped(['EST-SPE-12-01-A', 'EST-SPE-13-01-A', 'EST-SPE-14-01-A', 'EST-SPE-15-01-A', 'EST-SPE-16-01-A'])

## 05-GenIncidenceEstswithEPP
Milestone Title (Visible to User): | Milestone Description (Visible to User): |  | Entry Criteria: |  | Version:
Generate HIV incidence for generalized epidemics using EPP | UNAIDS Estimation and Projection Package is used in generalized epidemics to estimate HIV incidence for Spectrum. In this milestone, you will execute the steps needed to update your EPP projections from last year with new population, surveillance and survey data and then refit your projections. You will also distribute the newly calculated incidence across the age/sex bands under fit incidence ratios. |  | Country has a generalized epidemic and required data sets: ANC surveillance, survey (prevalence and incidence/ART coverage (if available), and routine ANC testing data |  | 0.2
Ref. | Task Title (Visible to User) | Task Test (if test passes, proceed to next test) | If test fails, present this to user: | Resources / Links | Mandatory right now | Comment | S4 Follow-up | Proceed to test (if test fails) | Test function
EPP-01-10 | Ensure pediatric and adult ART programme data inputs **have not** changed since you completed the first Spectrum milestone | Programme data for pediatric ART and adult ART have not changed since the first Spectrum milestone was completed? | You should be sure that Spectrum has your best, most up-to-date ART data. *If any underlying ART programme data have changed in your source files since you completed the first portion of Spectrum, you must return to the task in Spectrum where you enter your adult and pediatric ART data and then return to EPP.* | [5 empty] | check_manual_confirmation('EST-EPP-01-10-A')
EPP-02-01 | Define and review your country's epidemic structure in EPP | Has the user defined and reviewed the epidemic structure in EPP? | EPP requires the country to have a defined epidemic structure. You can see the previoulsy used epidemic structure for your country in Spectrum (Modules>AIM>Incidence>Configuration (EPP)) If all the information is valid, you can choose "Save and continue", which will take you to EPP's "Define Pops" page. If the epidemic structure is not correct, you can set it up according to data availability for your country. Once completed, choose "Save and continue" to proceed to the next step. |  |  | MM: I don't think EPP-03 and EPP-04 should be mandatory because they usually do not change |  |  | check_manual_confirmation('EST-EPP-02-01-A')
EPP-03-01 | Define population sizes for the epidemic structure | Has the user defined population sizes based on the selected epidemic structure? | If the epidemic structure is defined, population sizes must be entered for each population. In most cases you will not have to change this unless there is new data. Option 1: Divide National epidemic into urban/rural. Click Save and Continue. Option 2: For urban/rural structure epidemic with extended years of projections, you can either fill in percentage urban for extended years or adjust to UN values then click Save and Continue. Option 3: In case of National epidemic structure consisting of multiple sub-national projections, adjust for changed population, adding data for extended years, if necessary. Verify that population still to assign is 0 for all years then click Save and Continue. |  |  | MM: I don't think EPP-03 and EPP-04 should be mandatory because they usually do not change |  |  | check_manual_confirmation('EST-EPP-03-01-A')
EPP-04-01 | Enter new or corrected surveillance or survey data into EPP (if available) | Have you entered your prevlanece data from routine ANC and any other new surveillance or survey data? | Enter the latest ANC prevalence or any new survey or surveillance data into EPP under Incidence > Surveillance data (EPP). If you have new surveillance data to enter: i) select first subpopulation, ii) choose the HIV data mode for the source of your surveillance data (HIV Sentinel Surveillance or Antenatal Clinics), iii) enter data for sentinel and/or routine testing and census-level ANC if available. If applicable, continue this process for all sub-populations. If you have no survey data, click "Save and Continue". However, if you have new survey data, begin by clicking the "Source" button to explain the survey. Select the new survey, provide a short name, enter the year of the survey, and provide the standard error. If the survey has incidence, you can enter those values. Repeat for all sub-areas as needed. Once you have finished, click "Save and Continue" to proceed. |  | 1 |  |  |  | check_manual_confirmation('EST-EPP-04-01-A')
EPP-05-01 | Run curve fitting in Spectrum | Has the user run curve fitting in Spectrum? | An important step in estimating HIV incidence is curve fitting, which is completed in Spectrum (AIM > Incidence > Curve Fitting). Be sure to review your data in the graph on this page for each population before proceeding with the curve fitting process. If you see any outliers or mistaken data points in the surveillance, survey, or census data displayed on the graph, then return to "AIM > Incidence > Surveillance Data (EPP)" menu and correct them before fitting. Once you are satisfied with the data, you can select the model for fitting each population. In most instances this is the same model you have used in the previous year and no action is needed. You may consult the Guide 3, Spectrum Quick Start for information about which model to use. Once the model is selected for each population, set to run national projection and then "Fit All". Save All projections and calibrate if needed (Guide 3, Spectrum Quick Start can provide further information about calibration). Review the results on EPP’s “Fitting Results” page. Compare new results with previous projection using the “Compare” button. If there are large differences in the curve produced in the last round consider whether the input data or model fit might have changed those data. | Guide 3, Spectrum Quick Start https://hivtools.unaids.org/hiv-estimates-training-material-en/ | 1 | S4: To confirm, this is the Spectrum Quick Guide, correct? Also, note there's no direct link to the training materials and guides so I'm sending them to the landing page for the training material. MM: That is correct it is the spectrum quick start guide. We could send them to the EPP video: Training material ID Code G.21 or G.40 |  |  | check_manual_confirmation('EST-EPP-05-01-A')
EPP-06-01 | In Spectrum, restore sex/age incidence patterns to default values and fit them as fixed or time-dependent ratios | Have sex/age incidence patterns been restored to default values and then fit either as fixed over time or time-dependent ratios in Spectrum? | You are close to completing the Spectrum process. Ensure you have restored the default values for incidence ratios and then fit the incidence rate ratios either using fixed ratios or time-dependent ratios. For generalized epidemics with national surveys, the model will calculate the appropriate sex and age patterns. Begin by navigating to AIM > Sex/Age Pattern in Spectrum. Then click the button ‘Restore default values’. Then set the radio button to ‘Time dependent incidence ratios’ and click the button ‘Fit incidence’. The fit should only take a few minutes. Then set the radio button to ‘Fixed incidence ratios over time’ and click the button ‘Fit incidence ratios’ again. This fit should take only a minute or two. When it is done, look at the values of the Akaike information criterion for each option. This statistic measures the goodness of fit and adjusts for the degrees of freedom. The lower number is the better option. Set the radio button to that option. |  | 1 |  |  |  | check_manual_confirmation('EST-EPP-06-01-A')

## 06-GenKOSShiny90
Milestone Title (Visible to User): | Milestone Description (Visible to User): |  | Entry Criteria: |  | Version:
Generate knowledge of HIV status using Shiny 90 | In this milestone, you will use Shiny 90 to estimate the proportion of people living with HIV who know their HIV+ status (KOS). KOS is the "first 90" of the 90-90-90 framework used globally in the fight against HIV. In this milestone, you will enter programme and survey data, run your model, and download the results before returning to Spectrum. |  | Country has nationally representative population survey data with HIV serology testing; Spectrum file is completed (EPP run, and IRRs fit) highly recommended HTS data which have been reviewed and validated by the estimates team |  | 0.2
Ref. | Task Title (Visible to User) | Task Test (if test passes, proceed to next test) | If test fails, present this to user: | Resources / Links | Mandatory right now | Proceed to test (if test fails) | Test function | Comment | S4 Follow-up
S90-01-10 | Ensure pediatric and adult ART programme data inputs and incidence estimates for people living with HIV (EPP) have not changed since you completed your sex/age incidence patterns in Spectrum | Programme data for pediatric and adult ART as well as incidence results are up to date? | Shiny 90 will use the information on people living with HIV and numbers on ART in your Spectrum file to run the shiny90 model. If any of the data used in Spectrum have changed, please go back and update those data in Spectrum. If the ART or prevalence data have changed please rerun your EPP curve fitting. Once the Spectrum file is fully up to date you can run your Shiny 90 file |  |  |  | check_manual_confirmation('EST-S90-01-10-A')
S90-02-01 | Start a new working set in Shiny 90 | Is the user planning to start a new working set? | If you do not plan to start a new working set in Shiny 90, you must upload an existing work set to begin. You can upload either an existing working set or a new working set on the Shiny 90 home page. | Shiny 90 https://shiny90.unaids.org/ | 1 |  | check_manual_confirmation('EST-S90-02-01-A')
S90-03-CK |  | Are GEN-07-01, ADR-02-01, ADR-06-01, and EPP-06-01 complete? |  |  |  |  | check_not_skipped(['EST-GEN-07-01-A', 'EST-ADR-02-01-A', 'EST-ADR-06-01-A', 'EST-EPP-06-01-A']) | not a user facing task
S90-04-01 | Upload your final Spectrum file to Shiny 90 | Has the user uploaded a final Spectrum file to Shiny 90? | Shiny 90 requires you to have already completed the first milestone in Spectrum and download the final file. If you do not have a Spectrum file, you cannot yet begin the Shiny 90 process. Please return to Spectrum and complete all steps from milestone 01 - Input Data to Spectrum. |  | 1 |  | check_manual_confirmation('EST-S90-04-01-A')
S90-05-01 | Verify the Spectrum file you have uploaded by checking file name and visualizing the data in Shiny 90 | Has the user verified that the correct final, calibrated Spectrum file has been uploaded to Shiny 90 by checking the file name and visually reviewing the data in the graphics provided by Shiny 90? | Be sure to confirm you are using the correct Spectrum file by checking the file name and visually reviewing the data in the graphics provided by Shiny 90. If you have uploaded the incorrect Spectrum file, please upload the final file and then proceed. |  |  |  | check_manual_confirmation('EST-S90-05-01-A')
S90-06-01 | Upload your HIV Testing programme data file in the format required by Shiny 90 | Has the user uploaded an existing HIV Testing programme data file in the format required by Shiny 90? | Shiny 90 requires testing programme data in a specific format to function properly. Currently, the file can be downloaded from Shiny 90 after Upload the HIV Testing programme data file in the format required by Shiny 90 |  | 1 |  | check_manual_confirmation('EST-S90-06-01-A') | This template isn't available on ADR. It can't be validated by ADR currently. Shouldn't this be added to ADR and validated by the same? Note you cannot access it until after you upload your Spectrum file, meaning you have to disrupt the workflow to complete the file before proceeding with Shiny 90. @UNAIDS - we don't check if they've uploaded their survey file. Is this something we decided last week on the call? If not, I may have deleted by accident. Should we have an equivalent check for the survey file right after this one? Ian: the data checks and prep are under 01. yes this shoudl be validated there. the task here is for the user to load the program data
S90-07-01 | Visualize the programme data in Shiny 90 to confirm their validity | Has the user reviewed the programme data using the visualization options in Shiny 90 and confirmed the data are valid? | If you have not yet visualized the data to check for outliers or other data issues, please do so. Once you have visualized the data and confirmed data are of high quality, you may proceed with the Shiny 90 process. |  |  |  | check_manual_confirmation('EST-S90-07-01-A')
S90-08-01 | Run the Shiny 90 model | Has the user run the Shiny 90 model? | Now you are ready to run the model. You can run the model by clicking the Run Model link in the left menu and then the "Run Model" button. |  | 1 |  | check_manual_confirmation('EST-S90-08-01-A') | Ian: Question: at this point is the user in Navifator or in shiny 90? if in shiny 90 then steps 09-12 are repetious and not required as shiny 90 already guides the user to do these steps please demo via mock up what you envision here S4 20/Nov: although Shiny 90 (and other models such as Naomi) generally guides the user, the Navigator still provides the workflow and validates the status of the individual tasks (or asks the user to validate the task status). It also provides more detailed instructions than the main UI of the models. If we don't show the Navigator tasks step-by-step here, then it will be a different workflow than all other milestones. We'd like for users to be able to go back and forth between the models and Navigator and using Navigator to manage their progress. MM 24/Nov: Let's keep in for now. For next Navigator version, let's establish a principle for what stays in Navigator and what can be explained in the models themselves. For example, will Navigator take over quick start guides? Navigator currently covers 80% of quick start guides. Should we leave as is or cover remaining 20% and remove the guides?
S90-09-01 | Confirm Shiny 90 model outputs | Is the user satisfied with the model outputs after examining the visualizations presented by Shiny 90? | After you have viewed the advanced visualizations of the model outputs ("Advanced Outputs" tab), are you satisfied with the results? If you believe the model outputs do not reflect your expectations, you can determine underlying causes of poor outputs (e.g., survey data, programme data, Spectrum file), correct them and return to the beginning of Shiny 90. Once you are satisfied with the model outputs, you can download the Shiny 90 output file by clicking the "Download Shiny 90 Outputs for Spectrum" and return to Spectrum to proceed with the estimates process. |  |  |  | check_manual_confirmation('EST-S90-09-01-A')
S90-10-01 | Download the Shiny 90 output file for use in Spectrum | Has the user downloaded the Shiny 90 output file? | Now you are ready to download your results and return to Spectrum to continue the process. Click the "Download Shiny 90 Outputs for Spectrum” button and save the file in your preferred location then return to Spectrum to continue. |  | 1 |  | check_manual_confirmation('EST-S90-10-01-A')
S90-11-01 | Confirm PMTCT, ANC, pediatric ART, adult ART programme data inputs **have not changed** | Program data for PMTCT, ANC, pediatric ART, adult ART, and others required by Spectrum have not changed since the first Spectrum milestone was completed? | If any underlying programme data have changed since you completed the first portion of Spectrum, you must return to the beginning of the Spectrum process and repeat all steps before using Shiny 90. |  |  |  | check_manual_confirmation('EST-S90-11-01-A')

## 07-FinalizeNatlEstsSpectrum
Milestone Title (Visible to User): | Milestone Description (Visible to User): |  | Entry Criteria: |  | Version:
Finalize National HIV Estimates in Spectrum | In this milestone, you will finalize your national estimates using Spectrum. For countries producing provincial or state-level estimates in Spectrum the tasks must be completed for each of your Spectrum files. |  | Milestones, 1, 2, 3, 4, 5 and 6 are completed |  | 0.2
Ref. | Spectrum Check File Ref | Task Title (Visible to User) | Task Test (if test passes, proceed to next test) | If test fails, present this to user: | Resources / Links | Mandatory right now | Proceed to test (if test fails) | Test function | Comments | S4 Follow-up
SPF-01-10 |  | Confirm PMTCT, ANC, pediatric ART, adult ART programme data inputs have not changed since beginning the EPP process | No updates have been made to any Spectrum data files or underlying data to be used by Spectrum before using those files in models which project knowledge of status (population, PMTCT, ANC, ART, breastfeeding patterns)? | If any underlying programme data have changed since you completed the first portion of Spectrum, you must update the data entry in Spectrum, rerun EPP curve fits, and rerun shiny90. |  |  |  | check_manual_confirmation('EST-SPF-01-10-A') | JS: Spectrum will display whether the Uncertainty Analysis and Shiny 90 projections are Valid. If not, they need to be re-run. This is included in the Data Checker validation file we will send to ADR.
SPF-02-01 |  | Confirm no updates have been made to the HIV Testing programme data | No updates have been made to any Shiny 90 programme (HIV Testing) or survey data since completing the Shiny 90 process? | If any underlying programme or survey data have changed since you completed the Shiny 90 model, you must return to the beginning of the Shiny 90 process and repeat all steps before proceeding with the final stages of Spectrum. |  |  |  | check_manual_confirmation('EST-SPF-02-01-A') | JS: There no way for Spectrum to know this.
SPF-03-01 | Shiny90Valid,PedKOS_current,MaleKOS_current,FemaleKOS_current | Upload a completed Shiny 90 file to Spectrum or enter KOS estimates in another format | User's Spectrum file has updated knowledge of status data in Spectrum for current estimates year [required / optional data elements available in Indicator Element Matrix] by uploading a completed Shiny 90 file? | Each of your Spectrum files requires updated knowledge of status data elements for current estimates year using one of available options - Direct Entry of Case Reports, Shiny 90, CSAVR, ECDC, Manual Entry. Most countries will use Shiny 90. If you have used Shiny 90, you must upload your Shiny 90 model outputs (AIM > Program Statistics > Knowledge of Status > Data Source = Shiny 90 > Load Data). |  | 1 |  | check_manual_confirmation('EST-SPF-03-01-A') | JS: KOS must be run for each Spectrum file MM: Delete this row as it repeats the last step of KOS S4 20/Nov: The final tasks of KOS are downloading the file. This task is actually uploading it to Spectrum (or entering KOS through other means). Not sure why we drop this step as it's required. |  | DROP
SPF-04-01 |  | Confirm incidence estimates have been completed using EPP | Estimated incidence has been completed using EPP? | Your Spectrum file requires updated incidence estimates for the current estimates year. For 2022, only countries with generalized epidemics using EPP are using the HIV Estimates Navigator. Ensure you have completed the EPP process for generalized epidemics prior to proceeding in Spectrum. If you used another method to complete your incidence estimates, you can market this task complete. |  | 1 |  | check_manual_confirmation('EST-SPF-04-01-A') | UNAIDS: For 2022, Navigator is only available to countries with generalized epidemics using EPP.
SPF-05-01 |  | View and validate your Spectrum results | User has viewed and validated results of the model in Spectrum? | Ensure you have viewed and validated your country's results using Spectrum validation tab for all Spectrum files. There are a number of options for validating the Spectrum projection against data on the validation tab. The prevalence by age chart will compare the Spectrum estimate of prevalence by age (solid line) against survey estimates from the same year. You can select the survey in the drop-down menu at the top to pull in prepopulated data from the survey. Generally the Spectrum line should pass through the confidence intervals of the survey estimates. If you entered the number of people on ART by age group under Program Statistics, you can compare the Spectrum estimate (solid line) with those data. Under the ART option, you can display a chart showing the number of people living with HIV but not on ART according to whether they have never or previously been on treatment. In many countries today, the majority of those not on ART were in treatment previously but dropped out. The projections in this chart depend on the assumptions summarized at the bottom of that page about annual retention on ART, on the likelihood of re-initiation on treatment and whether mortality while off ART is different among those who were previously on treatment compared to those who are treatment naïve. You can change any of these assumptions to see the effect on the curves. Finally in the validation tab you can check the file completeness. This will ensure that the you have entered the required data for 2021, the parameters are updated to the latest defaults, and that you have the required additional files. Please make this final check before uploading to ADR. |  | 1 |  | check_manual_confirmation('EST-SPF-05-01-A')
SPF-06-01 | AdultARTcovLT100,PedARTcovLT100,PMTCTcovLT100 | Confirm your ART and PMTCT coverage does not exceed 100% | Coverages for adult and pediatric ART and PMTCT do not exceed 100%? | Occasionally, Spectrum will produce coverage of over 100% for ART or PMTCT services. There are multiple causes for coverage results over 100%. UNAIDS recommends consulting your estimates facilitator and/or UNAIDS to determine how to address coverage issues in your model results. |  | 1 |  | check_manual_confirmation('EST-SPF-06-01-A')
SPF-07-01 |  | Compare your Spectrum outputs to last year's results in read-only | Has user opened the prior year's file as read-only and compared it against the reporting period's results? | As a final step you can compare your new estimate for 2021 with the 2020 estimate prepared last year. To do this, choose ‘File’ from the top horizontal menu and then ‘Read Only’. (In the web version go to ‘Library’, click the ‘…’ menu next to last year’s file name and select ‘Read Only’. Spectrum will open last year’s projection in Read Only mode, meaning that you will not be able to change anything. Now when you display any result, you will see the new estimate shown in red and the previous estimate shown in blue. |  |  |  | check_manual_confirmation('EST-SPF-07-01-A') | JS: Good to suggest this, but it is not required.
SPF-08-01 | UAvalid | Run Uncertainty Analysis | Has user run Uncertainty Analysis? | The uncertainty associated with each result can be estimated using the Uncertainty Analysis tool. Access this tool by choosing ‘Tools’ from the top horizontal menu, then ‘More Tools’, then ‘Uncertainty analysis’. Set the ‘Aggregate data capture year’ to the final year of data and the ‘Number of iterations’ to 300, then click the ‘Process’ button. The model will run 300 simulations by choosing values for the epidemiological parameters from within their confidence intervals. This analysis may take 10-30 minutes. When it is complete, click the ‘Save’ button. After running this analysis you will see uncertainty intervals on all the outputs (as long as you only have one projection open in Spectrum). |  | 1 |  | check_manual_confirmation('EST-SPF-08-01-A')
SPF-09-01 |  | Confirm Spectrum results | User found no issues with Spectrum results? | Investigate and correct any underlying dataset or alter other parameters (e.g., sex/age patterns) and complete all subsequent steps in Spectrum for each affected Spectrum file. If underlying datasets change, all Spectrum steps - including knowledge of status and incidence estimates - must be repeated |  |  |  | check_manual_confirmation('EST-SPF-09-01-A')
SPF-10-01 |  | If you are using multiple Spectrum files (e.g., for provincial estimates), view aggregate results | If producing multiple Spectrum files, the user has reviewed the combined results using the Spectrum aggregate function? | If you have multiple Spectrum files (e.g., provincial files), you must use the aggregate function to view combined national-level estimates. Begin by saving all Spectrum files to a single location (e.g., your computer or share drive). Close all the files in Spectrum, click on Tools > More Tools > Aggregate. Choose the files to add and Process. If you are not producing sub-national estimates in Spectrum, mark this task complete. |  |  |  | check_manual_confirmation('EST-SPF-10-01-A')
SPF-11-01 |  | Upload your Spectrum file to your organization on ADR | Final, validated Spectrum file has been uploaded to the correct organization on ADR? | Before proceeding, you should now upload your final Spectrum file to the AIDS Data Repository (adr.hivtools.org). Saving your file to ADR supports sound knowledge management and will allow your country estimates team and supporters (e.g., UNAIDS) to view the results. Further, if you are proceeding with sub-national estimates, Naomi will require your Spectrum file. Naomi can pull your Spectrum file directly from ADR. To upload your Spectrum file to ADR, proceed to adr.hivtools.org and find your organization (i.e., country). In your country's list of data, you will see the Inputs Package for the reporting period. | AIDS Data Repository http://adr.hivtools.org | 1 |  | check_manual_confirmation('EST-SPF-11-01-A') | js: We are working on adding that capability. S4: @Fjelltopp - Link directly to the user's organization page and possibly Inputs Package for the current year. Ian: at this point there should be an autmated check to verify that the default parameters have been used, as well as check shiny file has loaded into Spectrum and comparison of ART totals to Naomi input files S4 20/Nov: we are checking default parameters at the end of the 1st Spectrum milestone, which follows the workflow in the training materials. Should it be repeated here? Checking uploaded Shiny file is up above. The validation of Spectrum ART totals vis-a-vis Naomi data files is the first step in Naomi milestone. Should it be moved here. Also, Spectrum CSV data checker will validate some (all?) of these things.
SPF-12-01 |  | Confirm no underlying data inputs used for KOS have changed | No updates have been made to any Spectrum data files or underlying data to be used by Spectrum before using those files in models which project knowledge of status (population, PMTCT, ANC, ART, breastfeeding patterns)? | If any underlying programme data have changed since you completed the first portion of Spectrum, you must return to the beginning of the Spectrum process and repeat all steps before proceeding with the final steps of Spectrum. Note steps you followed to estimate incidence (e.g., EPP) and produce KOS outputs (Shiny 90) must also be repeated. |  |  |  | check_manual_confirmation('EST-SPF-12-01-A') | JS: Data checker should help here. JP: I'm gathering info about how the checker will assist so we can build that into Navigator.
SPF-13-01 |  | Alert UNAIDS that your Spectrum file is ready for review | User has shared Spectrum file with UNAIDS? | Congratulations on reaching this point in the estimates process! Please alert your UNAIDS focal point that the file is ready for review and is availble on ADR. |  |  |  | check_manual_confirmation('EST-SPF-13-01-A') | S4: Are results shared with UNAIDS now or after Naomi in case of sub-national estimates? MM: Should be before but often a fluid process.
SPF-14-01 |  | Determine if you will produce district-level estimates | User is producing district-level HIV estimates? | If you are not producing district-level estimates, congratulations, you have completed the estimates process. You may now use your results for other needs such as the PEPFAR data pack, DMPPT, national reporting, or other needs. |  | 1 |  | check_manual_confirmation('EST-SPF-14-01-A')

## 08-GenSubNatlEstsNaomi
Milestone Title (Visible to User): | Milestone Description (Visible to User): |  | Entry Criteria: |  | Version:
Generate District HIV Estimates Using Naomi | Countries generating district-level estimates utilize the Naomi model. In this milestone, you will create a project, import your Inputs Package from the AIDS Data Repository, and execute multiple steps to calibrate and run the model for your district estimates. This is the final milestone in the HIV Estimates Navigator. |  | User has a validated, final Spectrum file No underlying Spectrum data (e.g., surveillance, survey, or programme data) have changed since the Spectrum file was produced. User has uploaded validated programme data and survey data files to ADR in the required formats |  | 0.2
Ref. | Naomi Check File Ref | Task Title (Visible to User) | Task Test (if test passes, proceed to next test) | If test fails, present this to user: | Resources / Links | Mandatory right now | Proceed to test (if test fails) | Test function | Comments | S4 Follow-up
NAO-01-10 |  | Upload Naomi data Inputs Package to ADR | Is the reporting period's estimates data Inputs Package uploaded to ADR and validated, including: i) Area boundary file, ii) Final, validated Spectrum file, iii) Population data, iv) Survey data, v) ART data, and vi) ANC data? | UNAIDS strongly encourages the use of ADR as the singular location for storing estimates data inputs. There are many advantages to using ADR, including the data validation feature which will ensure your data are in the required structure and meet basic data quality requirements. Naomi requires specific data inputs: i) Area boundary file, ii) Final, validated Spectrum file, iii) Population data, iv) Survey data, v) ART data, and vi) ANC data. Before beginning the Naomi process, UNAIDS recommends uploading these data inputs to this year's data Inputs Package to ADR. Naomi will then import these validated files directly from ADR. |  | 1 |  | check_manual_confirmation('EST-NAO-01-10-A')
NAO-02-01 | ART_is_Spectrum,ANC_is_Spectrum | Match data inputs for Spectrum and Naomi | Do all Naomi-required data which were also used by Spectrum or other models match the values used by Spectrum and other models? | Some data inputs used by Naomi are disaggregated versions of data inputs for other models such as Spectrum. For example, ART and ANC data used by Naomi are also used by Spectrum. You can learn more about the requirements for each of the models in 'Guide 8, Data quality, Indicator Element Matrix' in the UNAIDS training materials - https://hivtools.unaids.org/hiv-estimates-training-material-en/. It is critical that data inputs used by Naomi match the inputs used by Spectrum. Although in some cases disaggregation levels may differ, the sum of the disaggregations must equal those used by Spectrum. If the Naomi data inputs do not match those used in your Spectrum model process, modify them to match. If you have changed inputs used by Spectrum, you must return to Spectrum and begin the process again. If you have altered your Naomi inputs to match those used by Spectrum, you may continue with Naomi. |  | 1 |  | check_manual_confirmation('EST-NAO-02-01-A') | Ian: run a formal validation to compare the values in the spectrum file and the naomi input files @Fjelltopp - can ADR compare the Spectrum file's numbers and compare them to the Naomi Input Files?
NAO-03-01 |  | Create a Naomi user account | Does the user already have a Naomi account? | In order to take full advantage of Naomi's functionality, UNAIDS recommends you create a Naomi user account. A Naomi user account has multiple advantages, including integration with ADR and direct access to your Inputs Package, project saving, and sharing of draft and final project results. If you do not already have an account, you may request one by completing the brief Naomi user account request form. Responses should be immediate, especially during the time of estimates workshops. If you prefer, you may use Naomi as a guest, but it is not recommended. | Naomi user account request form https://forms.office.com/r/7S9EMigGr4 |  |  | check_manual_confirmation('EST-NAO-03-01-A')
NAO-04-01 |  | Log into Naomi | Is the user logged in to Naomi? | In order to take full advantage of Naomi's functionality, UNAIDS recommends you log into the system with your user account. There are many advantages to logging into Naomi such as integration with ADR and direct access to your estimates Inputs Package, project saving, and sharing of draft and final project results.. If you do not log in, you will not be able to pull your data from ADR nor save projects and versions. To log into Naomi, go to naomi.unaids.org. Click the 'Log in' button in the upper right corner of the home page to enter your login details. |  |  |  | check_manual_confirmation('EST-NAO-04-01-A')
NAO-05-01 | Package_created | Create a project in Naomi for the current reporting period | Has the user created a project in Naomi? | The first step to using Naomi is to create a project. Each Naomi project will have its own data and settings. If you are logged in, you can save multiple projects and test different data and model options for comparison. To create a project, simply enter a name for the project and click the 'Create Project' button. |  |  |  | check_manual_confirmation('EST-NAO-05-01-A')
NAO-06-01 | Package_has_all_data | Import validated data from ADR or by uploading directly to Naomi | Has the user imported validated data inputs either from ADR or through individual file uploads? | To begin the Naomi process, you must either import your data directly from ADR by entering your ADR access key or by uploading individual data input files required by Naomi. You can find your ADR access key on your ADR profile page (click your name in the upper part of any ADR page after logging in). You can find the required data file templates on ADR by searching the year and 'templates' (e.g., 2022 templates). *UNAIDS strongly recommends using last year's data files and updating them with data from the current reporting period.* Enter your data into these data files in the required formats and then either upload them to ADR for validation or directly to Naomi in order to proceed. You can also find more information about the required inputs for all models by accessing 'Guide 8, Data quality, Indicator Element Matrix' in the UNAIDS training materials. On the same page, you can find more information about preparing Naomi data inputs in 'Guide 4, Preparing Naomi data inputs'. | Guide 8, Data quality, Indicator Element Matrix https://hivtools.unaids.org/hiv-estimates-training-material-en/ | 1 |  | check_manual_confirmation('EST-NAO-06-01-A')
NAO-07-01 |  | Visualize inputs data in Naomi | Has the user visualized uploaded data and is the user satisfied with the results? | Naomi depends heavily on the quality of country data inputs. Modest data quality issues in these inputs may impact Naomi outputs significantly. Please visualize your data inputs in Naomi by scrolling through the various visualizations provided for survey and programme data. Be sure to use the filters provided to review specific portions of the data for validity. You can learn more about standards of practice for estimates data quality in Guide 6, Data Quality Standards of Practice in the UNAIDS estimates training materials. | Guide 6, Data Quality Standards of Practice in the UNAIDS estimates training materials https://hivtools.unaids.org/hiv-estimates-training-material-en/ |  |  | check_manual_confirmation('EST-NAO-07-01-A')
NAO-08-01 | Opt_recent_qtr,Opt_future_proj_qtr,Opt_area_ID_selected,Opt_calendar_survey_match,Opt_recent_survey_only,Opt_ART_coverage,Opt_ANC_data,Opt_ART_data,Opt_ART_attendance_yes | Select or confirm default settings in Naomi model options | Has the user selected or confirmed default settings in model options? | Naomi is a flexible model which allows countries to customize their subnational outputs. Review the multitude of model options available to users. You can learn more about these options in 'Guide 5, Naomi Quick Start' in UNAIDS estimates training materials. | Guide 5, Naomi Quick Start https://hivtools.unaids.org/hiv-estimates-training-material-en/ | 1 |  | check_manual_confirmation('EST-NAO-08-01-A') | Ian: Can we run a formal check on the naomi file that is uploaded to the ADR to verify if the standandirsed options a country has used match what is expecetd. This means we need a prepoulated database that contains a list of expected parameters for each country that uses naomi @Fjelltopp - possible this year?
NAO-09-01 | Model_fit | Fit the model in Naomi | Has the user fit their model in Naomi? | After you have selected and validated the various model options, the next step in the Naomi process is to fit your model. Depending on your underlying data, this step may take some time (up to 30 minutes or even an hour in rare cases). When you are ready, simply click the "Fit Model" button. |  | 1 |  | check_manual_confirmation('EST-NAO-09-01-A')
NAO-10-01 | Cal_PLHIV,Cal_ART,Cal_KOS,Cal_new_infections,Cal_method | Calibrate the model in Naomi | Has the user calibrated the model? | This should be done for the following four indicators (PLHIV, ART, aware of HIV status and new infections). This is to ensure that the mean aggregate estimates from Spectrum and Naomi are consistent. All these should be adjusted to match your Spectrum file either the national or sub-national Spectrum files with the following age sex stratification: (sex and age <15 /15+ years). Calibration method: use the default which is logistic and which scales the prevalence, ART coverage, proportion unaware, and incidence on the logit scale within each district / sex / age stratum in order to match to Spectrum. This ensures that ART coverage does not go above 100% in any district / sex / age stratification. Further information is available in Guide 5, Naomi Quick Start. | Guide 5, Naomi Quick Start https://hivtools.unaids.org/hiv-estimates-training-material-en/ | 1 |  | check_manual_confirmation('EST-NAO-10-01-A')
NAO-11-01 |  | Confirm **no** data files in your Inputs Package on ADR required for district estimates have changed since you began Naomi | No updates have been made to any Naomi data files or underlying data to be used by Naomi before using those files in models which project subnational est? | If any underlying programme data have changed since you completed the first portion of Spectrum, you must return to the beginning of the Spectrum process and repeat all steps before proceeding with the final steps of Spectrum. *Note steps you followed to estimate incidence (e.g., EPP) and produce KOS outputs (Shiny 90) must also be repeated if your underlying data files have changed.* |  | 1 |  | check_manual_confirmation('EST-NAO-11-01-A')
NAO-12-01 |  | Review your Naomi model output | Has user reviewed their Naomi model output? | Once you have calibrated your Naomi model, it's time to review the results in the maps and in the tables available through the Download function. Review coverage estimates for values that are over 100% or implausibly high; review prevalence and incidence data for values that are not realistic (e.g., outlying compared to most other districts or to other quarters/years). Currently available review options include: i) Visualisations - Chloropleth, Bar chart, Bubble plot; ii) Tabular results - Estimates and CIs, Sortable and searchable; iii) All stratifications of - Indicators, Levels, Areas, Time points, Sexes, and Age groups. If you have questions or concerns about your Naomi model outputs, contact your estimates facilitator or UNAIDS. |  |  |  | check_manual_confirmation('EST-NAO-12-01-A')
NAO-13-01 |  | Download your Naomi results | Has user downloaded their Naomi results? | Now it's time to download your results for review by UNAIDS, use in country-level and global reporting, country programme planning and use, and your PEPFAR Data Pack. There are three download options below. Ensure you have uploaded the final outputs to ADR for records retention and to allow access to the results to your country estimates team and other interested stakeholders (e.g., UNAIDS and your estimates facilitator). Options: 1. Export model outputs for Spectrum. Use this option to download a zip file which can then be uploaded into Spectrum and used to create a Data pack. You can also use this file to view the results on a Naomi-Spectrum viewer available at NaomiSpectrum.unaids.org. This provides some additional viewing options and a table format of the data both at district and province level. 2. Download coarse age group outputs. 3. Download summary report. This option provides a summary of your results which you can share with key stakeholders. |  | 1 |  | check_manual_confirmation('EST-NAO-13-01-A')
NAO-14-01 |  | Upload final validated Naomi file to your organization on ADR | Has user uploaded final validated Naomi files to ADR? | As a final step, you should now upload your final Naomi files to the AIDS Data Repository (adr.hivtools.org). Saving your file to ADR supports sound knowledge management and will allow your country estimates team and supporters (e.g., UNAIDS) to view the results. To upload your Naomi files to ADR, proceed to adr.hivtools.org and find your organization (i.e., country). In your country's list of data, you will be able to upload your files for the reporting period. Be sure to inform UNAIDS when you have uploaded your Naomi file to ADR for their review. | AIDS Data Repository http://adr.hivtools.org | 1 |  | check_manual_confirmation('EST-NAO-14-01-A')